## Sheet1
Sprint 1 Backlog
Team 5 - Kurtis Mulgrew, Calum Duncan, Rory Duthie and Neil Archibald
To do
In progress
Completed
Task Description | Duriation in hours | Who | Status | Thursday | Friday | Monday | Tuesday | Wednesday | Thursday
1. Analyse current code and get app to maintain current functions
Write acceptance test | 1 | Neil | Completed | 1 | 1 | 1 | 1 | 1 | 1
Find and evaluate errors in code | 2 | Kurtis | Completed | 2 | 1 | 1 | 1 | 1 | 1
Fix data scraping URL errors | 5 | Rory | Completed | 5 | 4 | 3 | 1 | 2 | 1
Run app on a simulator | 2 | Calum | Completed | 2 | 1 | 1 | 1 | 1 | 1
Run app on a android phone and tablet | 1 | Calum | Completed | 1 | 1 | 1 | 1 | 1 | 1
Present completed task to client | 1 | Rory | Completed | 1 | 1 | 1 | 1 | 1 | 1
2. Rank Shares in rank order
Write acceptance test | 2 | Calum | Completed | 2 | 2 | 2 | 2 | 2 | 2
Design table | 1 | Neil | Completed | 1 | 1 | 1 | 1 | 1 | 1
Write function to rank shares | 10 | Kurtis | In progress | 10 | 5 | 4 | 6 | 3 | 3
Display shares ranked on table | 5 | Rory | In progress | 3 | 5 | 3 | 2 | 1 | 3
Run function on Android phone and Tablet | 2 | Kurtis | To do | 0 | 0 | 0 | 0 | 0 | 0
Fix errors and handling | 3 | Rory | To do | 0 | 0 | 0 | 0 | 0 | 0
Present completed task to customer | 1 | Neil | To do | 0 | 0 | 0 | 0 | 0 | 0
Ideal - Remaning efforts in uninterrupted woring hours | 114 |  |  | 29 | 27 | 23 | 20 | 15 | 0
Actual - Remaning efforts in uninterrupted woring hours | 108 |  |  | 27 | 21 | 17 | 16 | 13 | 14